|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Month** | **2016** | **2017** | **2018** | **2019** |
| 01 | Literature Review | * Develop Prototype * 1st experiment * 2nd survey | * Update Prototype * 3rd experiment * 4th survey | Thesis writing |
| 02 |
| 03 |
| 04 | * **25-minute Seminar** * Questionnaire Design * 1st survey | **Progress Report** | **Thesis Audit** |
| 05 | (In Indonesia)   * Update Prototype * 2nd experiment * 3rd survey | (In Indonesia)   * Update Prototype * 4th experiment * 5th survey |
| 06 | Develop Prototype  (for modelling) |
| 07 |
| 08 |
| 09 | **Thesis Outline** |
| 10 | Develop Prototype  (metamodeling) | **40-minute Seminar** |
| 11 | **Qualifying Dissertation** | Thesis writing | **Thesis Submission** |
| 12 | Develop Prototype |